## Slide 1
Introduction
Our client's satisfaction is critical for us.
Orion Introduction

## Slide 2
Objectives
JAO engaged as part of their Corporate Strategic Objectives to improve explicit auction experiences.
A new Auction Platform with the following in mind:
User Experience: it must be fast, intuitive, appealing and streamlined
Stability and performance: it must be reliable and support market constraints whatever the volume
Integrability and automation: API first architecture design as part of its fundamentals for ease and standardization of integration.
Autonomy: integration of ease of life feature for clients
* Preliminary mockup design not reflecting the final product
Unicorn has been selected as the provider and the platform will be named Orion

## Slide 3
Roadmap
2025
2026
2027
Q2-2025-Q2 2026: Agile Design phase (Detailed specification, UX, UI, flows, integrations…)
Post-Q4 2027: Optimization and Ongoing Enhancements
Continue leveraging platform flexibility for continuous improvement.
Q4 2027:
hyper care
Q3 2025 -> Q4 2026:
Agile Implementation and validation phase
April 2025: project kickoff
01/2027 -> Q2/3 2027:
Testing phases (Int. TSOs, MPs…), training (Int. MPs, TSOs…), Operations readiness
Sept 2027:
Go-Live
Dec 2026:
Technical readiness and deployment
Q3 2027:
Data migration and Go-live sign-off
Q3 2026 -> Q4 2026:
Infrastructure setup and availability/recoverability
Q3 2025 -> Q2 2027:
Parallel project integration process

## Slide 4
Orion – The new allocation tool
Use cases
INVOICES
DASHBOARD
HARMONIZED AUCTION CALENDAR
DISPLAY AUCTIONS
User
Account management
NOTIFICATIONS
SETTLEMENTS
REST API

## Slide 5
Main Changes
No emails, output files
JSON-based payloads via REST API
Machine users hold certificate
Dashboard
Machine users hold certificate
Multi Factor Authentication
Primary Authorized Person
What are the new API, is there any change in the xml structure?

## Slide 6
Upcoming Activities
Connectivity test – Phase 1
With three User Group members
‘26 Sept.
Connectivity test – Phase 2
With all User Group members
‘26 Nov.
Connectivity test – Phase 3
With every Market Participants
‘27 Jan.

## Slide 8
JAO Support Hub

## Slide 9: JAO Support Hub
More than a ticketing platform
Ticketing
Registration
Account management
Digitalized, seamless processes

## Slide 11
Q & A

## Slide 12
Thank you!