## Slide 1
Introduction
Our client's satisfaction is critical for us.
Open Call 08.09.2026

## Slide 2
Introduction

## Slide 3
Agenda
2. Auction Calendar
3. Short News
4. Orion
6. Q & A
5. JAO Support Hub
1. Projects overview

## Slide 4
Projects overview

## Slide 5
Projects
Intraday Auction on the Ukrainian borders (?)
JAO Support Hub
2026
PTR to FTR switch on North Italy borders IT<>AT, IT<>FR, IT<>SI
21.09
North Sea Link Long-term auctions
17.09
Long Term Flow Based Allocation
30.11
North Sea
Project Pelagonia GR-MK Explicit auctions
November
01.01

## Slide 6
LTFBA Status Overview
Highlights
eCAT:
  eCAT Development of the baseline scope and the additional change request package have been completed
  Training and 2 Rounds of Functional Testing completed successfully with signoff from all TSOs and RCCs
  Procedural Testing in progress – Rounds 1, 2 and 3 completed – 4th round due for completion mid September
Publication Tool:
  Development for Core and Nordics Completed as per approved scope with some final clarifications pending on Nordics Congestion Income Page.
  Files now being sent by Nordic RCC successfully and Functional Testing is in Progress.
External Parallel Run:
  LTFBA and LTCC combined parallel run in progress.
SAP (Invoicing Tool):
  Implementation Guide Approved
  Development on Track and aligned with Testing timeline.
  Post coupling process not linked to regulatory milestone for LTFBA

## Slide 7: Roadmap
Activity​ | Aug​ 25​ | Sep​ 25​ | Oct​ 25​ | Nov​ 25​ | Dec​ 25​ | Jan​ 26​ | Feb​ 26​ | Mar​ 26​ | Apr​ 26​ | May​ 26​ | Jun​ 26​ | Jul​ 26​ | Aug​ 26​ | Sep​ 26​ | Oct​ 26​ | Nov​ 26​ | Status​
Simulation Platform​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | 100%​
eCAT​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | 70%​
MP Testing*​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | 70%​
Website & Publication Tool​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | 80%​
Go Live (Regulatory)​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ | ​
*2 rounds of MP Testing completed in July and August. A third round will be taking place from the 4th of September.
Ahead of each activity JAO will formally issue comms to Market Participants with more information regarding their involvement. Dates are to be confirmed but will include timings and details of workshops and alignments, engagement forums and format.
Test w. MPs
SIT – RCCs, TSOs
SIT – RCCs, TSOs
9th & 10th
5th & 6th
4th , 9th & 10th
LTCC and LTFBA Publication Tool Ext Parallel Run

## Slide 8: LTFBA Supporting documents
ACER and ENTSO-E organized online workshops regularly to align on strategically important topics shaping the long-term flow-based allocation of transmission capacities.
So far, 8 workshops have been organized. The topics and supporting documents of these workshops, including the links of the event pages available on JAO’s website.

## Slide 12
Short News

## Slide 13
Short News
Public release notes
New Feedback collections approach -No more Annual Surveys
15 Min MTU new roadmap is under assessment

## Slide 14
Auction Calendar

## Slide 15
Certificate reviewal
Credit limit management
Auction Calendar 2027 in mid-October
Y+2 auction Switzerland – Italy auction

## Slide 16
16.09.2026
15.09.2026
16.09.2026
Spain-France Y Base 1 – 2027
Nemolink Y Base 8 – 2027
Viking Link Y Base 3 – 2027
23.09.2026
Denmark – Netherland Y Base 1 – 2027
Auction Calendar
23.09.2026
IFA2 Y Base 6 – 2027
24.09.2026
Switzerland - France Y Base 2 – 2027
2027

## Slide 17
09.09.2026
10.09.2026
16.09.2026
IFA1 Y Base 2 – 2028
Eleclink Y Base 4 – 2028
Eleclink Y Base 3 – 2028
22.09.2026
Nemolink Y Base2 – 2028
Auction Calendar
13.10.2026
IFA2 Y Base 2 – 2027
17.11.2026
Nemolink Y Base 3 – 2028
2028

## Slide 18
Orion

## Slide 19
Objectives
JAO engaged as part of their Corporate Strategic Objectives to improve explicit auction experiences.
A new Auction Platform with the following in mind:
User Experience: it must be fast, intuitive, appealing and streamlined
Stability and performance: it must be reliable and support market constraints whatever the volume
Integrability and automation: API first architecture design as part of its fundamentals for ease and standardization of integration.
Autonomy: integration of ease of life feature for clients
* Preliminary mockup design not reflecting the final product
Unicorn has been selected as the provider and the platform will be named Orion

## Slide 20
Roadmap
2025
2026
2027
Q2-2025-Q2 2026: Agile Design phase (Detailed specification, UX, UI, flows, integrations…)
Post-Q4 2027: Optimization and Ongoing Enhancements
Continue leveraging platform flexibility for continuous improvement.
Q4 2027:
hyper care
Q3 2025 -> Q4 2026:
Agile Implementation and validation phase
April 2025: project kickoff
01/2027 -> Q2/3 2027:
Testing phases (Int. TSOs, MPs…), training (Int. MPs, TSOs…), Operations readiness
Sept 2027:
Go-Live
Dec 2026:
Technical readiness and deployment
Q3 2027:
Data migration and Go-live sign-off
Q3 2026 -> Q4 2026:
Infrastructure setup and availability/recoverability
Q3 2025 -> Q2 2027:
Parallel project integration process

## Slide 21
Orion – The new allocation tool
Use cases
INVOICES
DASHBOARD
HARMONIZED AUCTION CALENDAR
DISPLAY AUCTIONS
User
Account management
NOTIFICATIONS
SETTLEMENTS
REST API

## Slide 22
Main Changes
No emails, output files
JSON-based payloads via REST API
Machine users hold certificate
Dashboard
Machine users hold certificate
Multi Factor Authentication
Primary Authorized Person
What are the new API, is there any change in the xml structure?

## Slide 23
Upcoming Activities
Connectivity test – Phase 1
With three User Group members
‘26 Sept.
Connectivity test – Phase 2
With all User Group members
‘26 Nov.
Connectivity test – Phase 3
With every Market Participants
‘27 Jan.

## Slide 25
JAO Support Hub

## Slide 26: JAO Support Hub
More than a ticketing platform
Ticketing
Registration
Account management
Digitalized, seamless processes

## Slide 28
Q & A

## Slide 29
Thank you!